## Sheet1
Item | P | I | Risk (P*I) | Recognized | Mitigated/ Resolved | ROAM | How
Simplicity Errors when adding sources for LCD | 3 | 20 | 60 | 2021-10-29 | Mitigated | M | Use the LCD example provided by Nick as the baseline
Gecko keeps issuing errors when debugging | 5 | 20 | 100 | 2021-10-29 |  | O | No way to resolve this issue. Debugger always disconnects
Gecko becomes bricked | 1 | 100 | 100 | 2021-11-05
0
0
0
0
0
0

## Sheet2
Valid Modified Fibonacci values
1
2
3
5
8
13
20
40
70
100